## Development Log
Development Log
Date | Time | Meeting NO. | Activity | Members Present | Progress Made | Decisions Made
27th July, 2026 | 20:00:00.0000000000031950 | 1 | Initial team meeting to discuss the DSA semester project and understand the project requirements | 1. Patience Owusu 2.Emmanuel Grant Boamah 3.Micheal Obiri 4.Abdul Raziq 5.Ethan Bill 6.Tossou Bridget Fafa 7.Christian Agyapong 8.Mackey Kumi | Team discussed the project requirements and deliverables. | Agreed to review the project instructions and meet again to assign roles.
2026-07-28 | 20:00:00.0000000000031950 | 2 | Team planning and role assignment meeting | 1.Boamah Emmanuel Grant 2. Patience Owusu 3. Mackey Kumi 4.Eshun Jeffrey 5.Tossou Bridget Fafa 6.Abdul-Raziq Nyaaba Shahad 7.Desmond Pinamang Aikins 8.Christian Agyapong 9.Kimathi Jojo Gator 10.Lord Fianu | The team assigned roles and responsibilities, discussed how the project would be organized, and agreed on the tasks each member would complete. | Roles were assigned based on members' strengths, and members agreed to begin working on their assigned tasks before the next meeting.
2026-08-03 | 20:00:00.0000000000031950 | 3 | Work plan presentation and progress review | 1. Boamah Emmanuel Grant 2. Owusu Patience 3. Tossou Bridget Fafa 4. Bill, Ethan Nii Addy 5.Amoah 6. Kimathi Jojo Gator 7.Addo Michael Obiri | The work plan was explained, and each member presented the work they had completed. | The team reviewed the work presented and agreed to continue with the assigned tasks according to the work plan.
2026-08-05 | 20:00:00.0000000000031950 | 4 | Project work plan and feature implementation discussion | 1. Boamah Emmanuel Grant 2.Abdul Raziq 3.Addo Michael Obiri 4.Joseph Kwaku Wiafe 5.Lord Fianu 6.Owusu Patience 7.Tossou Bridget Fafa | The team was taken through the project structure, GitHub repository setup, project features, and the data loader feature. The data requirements and the use of Java, CSV files, and a database were also discussed. | The team agreed to move from planning into implementation, join the GitHub organisation, work on assigned folders/features, and speed up development to meet the remaining project timeline.
2026-08-26 | 19:30:00.000 | 5 | Presentation and testing of completed work | 1. Boamah Emmanuel Grant 2. Bill, Ethan Nii Arday 3. Lord Fianu 4. Owusu Patience 5. Tossou Bridget Fafa 6. Joseph Kwaku Wiafe | Team members presented the work they had completed and shared their screens to demonstrate and test the functionality of their work. | The team agreed to continue working on their assigned tasks and provide updates on their progress in subsequent meetings.
2026-08-27 | 12:30:00.0000000000031950 | 6 | The team reviewed the progress of the development work. Members discussed testing the implemented features, running the necessary commands, and checking that the system was working correctly. Preparations for the project presentation and demonstration were also discussed. | 1.Boamah Emmanuel Grant 2.Abdul-Raziq Nyaaba Shahad B. 3.Tossou Bridget Fafa 4.Bill Ethan Nii Arday 5.Amoah 5.Joseph Kwaku Wiafe 6.Agyapong Christian 7Kimathi Jojo Gator 8.Owusu Patience | The team agreed to continue testing the work and ensure that the features were functioning properly. Members were also expected to prepare for the upcoming project presentation and demonstration. | Members should test their assigned features, confirm that their work is functioning correctly, and prepare their laptops for the project demonstration and presentation.